## Test summary report
Tester | Phan Thế Hoàng
Nguyễn Hoàng Phi Hùng
Nguyễn Lê Trúc Mai
Nguyễn Hiệp Thắng
Phan Hoàng Quang Nghị
Date | 2025-03-25
Test summary report
| Number of functions be tested | 24
| Number of test cases | 101
| Number of passed test cases | 91
| Number of failed test cases | 10
| Number of bugs | 10

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | The word card's information has not been updated correctly. | The word card information is not updated correctly when editing the vocabulary list even though the system displays successfully message. | [USC8] | High | Quang Nghị | 2025-03-08 | Closed
B002 | Creating untitle list when input invalid value | When input in valid value such as: 1 character in title, not input definition of vocabulary etc, then clicking "Create List", front end notify the error but when we check in "My vocabulary list" a untitle vocabulary list is display | [USC6] | High | Phi Hùng | 2025-03-08 | Closed
B003 | Sign up with wrong email format | Frontend should pop up Error: "Invalid email format" but nothing happens | [USC1] | High | Trúc Mai | 2025-02-08 | Closed
B004 | Classroom doesn't update info after each action | After performing a classroom action (accepting new learners, enabling auto approval), the classroom info doesn't update immediately, even after refreshing. The user need to navigate to the my classroom tab and enter the classroom again for the changes to be shown | [USC23] + [USC24] | Medium | Hiệp Thắng | 13/08/2025 | Closed
B005 | Classroom doesn't validate learner email | When inviting the learner to the classroom, if the teacher enters an invalid email, the frontend doesn't validate email format leading to an error when attempting to send the email | [USC15] | High | Hiệp Thắng | 13/08/2025 | Closed
B006 | Clicking 'Review' Button of an assignment in My Classroom | When the learner clicks the "Review" button on an assignment, the system does not respond or navigate to the Review page. This occurs because the frontend has not yet been integrated with the Review section. | [USC22] | Medium | Trúc Mai | 25/08/2025 | Open
B007 | Missing Progress Chart in Statistics Section | When teacher views the statistics for an assignment, the system does not display the weekly average progress chart or individual progress charts for each learner. This happens because the frontend has not yet implemented the progress chart feature. | [USC24] | Low | Trúc Mai | 25/08/2025 | Open
B008 | User's status is not updated when admin approve request | When admin click approve a teacher request, the account status of the owner of request does not update from "pending_verification" to "active" | [USC16] | Medium | Thế Hoàng | 25/08/2025 | Open
B009 | User's status is not updated when admin decline reuest | When admin click approve a teacher request, the account status of the owner of request does not update from "pending_verification" to "inactive" | [USC16] | Medium | Thế Hoàng | 25/08/2025 | Open
B010 | Cannot search teacher request by owner's email | When admin search teacher request by owner email, do not have any search result | [USC16] | Medium | Thế Hoàng | 25/08/2025 | Open
B011 | The deleted word does not dissapear in user's vocabulary list | The word was deleted by admin still in the user's vocabulary list | [USC17] | Medium | Thế Hoàng | 25/08/2025 | Open
Note on D1: ====== ID#AAABmlhhL-8 Vu V. Nguyen (2025-07-18 09:16:31) Function ID of the function where the defect is found
Note on E1: ====== ID#AAABmlhhL_A Vu V. Nguyen (2025-07-18 09:16:31) High, Medium, or Low
Note on F1: ====== ID#AAABmlhhL_E Vu V. Nguyen (2025-07-18 09:16:31) Name of the tester who reports the defect
Note on H1: ====== ID#AAABmlhhL-4 Vu V. Nguyen (2025-07-18 09:16:31) Open or Closed